## Gantt Chart Template
| PROJECT TITLE | Medication Visualizer 2 - CS 6440 |  |  |  |  | INITIATION | [6 empty] | PROJECT DESIGN | [34 empty] | FIRST PHASE OF PROJECT IMPLEMENTATION | [20 empty] | SECOND PHASE OF PROJECT IMPLEMENTATION | [27 empty] | FINALIZING
| PROJECT MANAGER | Dasom Eom |  |  |  |  | SPRINT ONE | [6 empty] | SPRINT TWO | [16 empty] | SPRINT THREE | [17 empty] | SPRINT FOUR | [6 empty] | SPRINT FIVE | [6 empty] | SPRINT SIX | [6 empty] | SPRINT SEVEN | [13 empty] | SPRINT EIGHT | [6 empty] | SPRINT NINE | [6 empty] | SPRINT TEN
# | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | Status | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 13 | [6 empty] | WEEK 14 | [6 empty] | WEEK 15
[7 empty] | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U
| Medication Visualizer | Team Apollo | 2020-01-20 | 2020-04-20 | 90 | 70%
1 | Team Sprint #1 |  | 2020-01-20 | 2020-01-27 | 7 | 100% | bar: WEEK 1 M to WEEK 1 U
1.1 | Topic Selection | All | 2020-01-20 | 2020-01-27 | 7 | 100% | bar: WEEK 1 M to WEEK 1 U
1.2 | Team Confirmation | All | 2020-01-20 | 2020-01-27 | 7 | 100% | bar: WEEK 1 M to WEEK 1 U
2 | Team Sprint #2 |  | 2020-01-27 | 2020-02-13 | 16 | 100% | bar: WEEK 2 M to WEEK 4 W
2.1 | Research | All | 2020-02-05 | 2020-02-13 | 8 | 100% | bar: WEEK 3 T to WEEK 4 W
2.2 | Preparing Gantt Chart | Patrick, Uday | 2020-02-05 | 2020-02-13 | 8 | 100% | bar: WEEK 3 T to WEEK 4 W
2.3 | Documenting Project Plan | Dasom, Uday | 2020-02-10 | 2020-02-13 | 3 | 100% | bar: WEEK 3 U to WEEK 4 W
2.4 | Architectural Diagram | Uday | 2020-02-10 | 2020-02-13 | 3 | 100% | bar: WEEK 3 U to WEEK 4 W
2.5 | PowerPoint | Dasom | 2020-02-10 | 2020-02-13 | 3 | 100% | bar: WEEK 3 U to WEEK 4 W
2.5.1 | Presentation | Rory | 2020-02-12 | 2020-02-13 | 1 | 100% | bar: WEEK 4 W
3 | Team Sprint #3 |  | 2020-02-13 | 2020-02-24 | 11 | 100% | bar: WEEK 4 R to WEEK 6 U
3.1 | Research | All | 2020-02-13 | 2020-02-24 | 11 | 100% | bar: WEEK 4 R to WEEK 6 U
3.2 | Deciding Stack and Tools | All | 2020-02-19 | 2020-02-20 | 1 | 100% | bar: WEEK 5 W
3.3 | Prototype | Rory | 2020-02-19 | 2020-02-24 | 5 | 100% | bar: WEEK 5 W to WEEK 6 U
3.4 | Initiating Deployment Pipeline | Patrick | 2020-02-19 | 2020-02-24 | 5 | 100% | bar: WEEK 5 W to WEEK 6 U
3.5 | Gantt Chart Update | Uday | 2020-02-19 | 2020-02-24 | 5 | 100% | bar: WEEK 5 W to WEEK 6 U
3.6 | PowerPoint | Dasom, Uday | 2020-02-19 | 2020-02-24 | 5 | 100% | bar: WEEK 5 W to WEEK 6 U
3.6.1 | Presentation | Rory, Marco | 2020-02-22 | 2020-02-24 |  | 100% | bar: WEEK 6 S to WEEK 6 U
4 | Team Sprint #4 |  | 2020-02-24 | 2020-03-02 | 8 | 100% | bar: WEEK 7 M to WEEK 7 U
4.1 | Team Meeting with TA | All | 2020-02-26 | 2020-02-27 | 1 | 100% | bar: WEEK 7 W
4.2 | Research | All | 2020-02-24 | 2020-02-27 | 3 | 100% | bar: WEEK 7 M to WEEK 7 W
4.3 | Fetch Data using the API | Uday | 2020-02-25 | 2020-03-02 | 7 | 100% | bar: WEEK 7 T to WEEK 7 U
4.4 | Basic UI Setup | Uday | 2020-02-25 | 2020-03-02 | 7 | 100% | bar: WEEK 7 T to WEEK 7 U
4.5 | Gantt Chart Update | Dasom | 2020-02-24 | 2020-03-02 | 8 | 100% | bar: WEEK 7 M to WEEK 7 U
4.6 | Status Update Report | Dasom | 2020-02-29 | 2020-03-02 | 2 | 100% | bar: WEEK 7 S to WEEK 7 U
4.7 | Experiment on deployment of HDAP | All | 2020-02-24 | 2020-03-02 | 8 | 100% | bar: WEEK 7 M to WEEK 7 U
4.8 | Hello World of HDAP | Patrick, Dasom | 2020-02-24 | 2020-03-02 | 8 | 100% | bar: WEEK 7 M to WEEK 7 U
5 | Team Sprint #5 |  | 2020-03-02 | 2020-03-09 | 7 | 100% | bar: WEEK 8 M to WEEK 8 U
5.1 | Hello World of HDAP - Continued | Patrick, Dasom | 2020-03-02 | 2020-03-05 | 3 | 100% | bar: WEEK 8 M to WEEK 8 W
5.2 | Deploying the initial product on HDAP | Uday | 2020-03-05 | 2020-03-09 | 4 | 100% | bar: WEEK 8 R to WEEK 8 U
5.3 | Research on React JS and HDAP | All | 2020-03-02 | 2020-03-09 | 7 | 100% | bar: WEEK 8 M to WEEK 8 U
5.3 | Gantt Chart Update (new version) | Dasom | 2020-03-02 | 2020-03-07 | 5 | 100% | bar: WEEK 8 M to WEEK 8 F
5.4 | Dev Progress Check with TA | Dasom | 2020-03-02 | 2020-03-07 | 5 | 100% | bar: WEEK 8 M to WEEK 8 F
5.5 | Status Update Report | Dasom | 2020-03-02 | 2020-03-07 | 5 | 100% | bar: WEEK 8 M to WEEK 8 F
6 | Team Sprint #6 |  | 2020-03-09 | 2020-03-16 | 7 | 100% | bar: WEEK 9 M to WEEK 9 U
6.1 | Team Meeting | All | 2020-03-11 | 2020-03-12 | 1 | 100% | bar: WEEK 9 W
6.2 | Research | All | 2020-03-09 | 2020-03-13 | 4 | 100% | bar: WEEK 9 M to WEEK 9 R
6.3 | Update Prototype | Uday, Dasom, Patrick | 2020-03-09 | 2020-03-14 | 5 | 100% | bar: WEEK 9 M to WEEK 9 F
6.4 | Progress Report | See Below | 2020-03-09 | 2020-03-16 | 7 | 100% | bar: WEEK 9 M to WEEK 9 U
6.4.1 | PowerPoint | Dasom | 2020-03-09 | 2020-03-15 | 6 | 100% | bar: WEEK 9 M to WEEK 9 U
6.4.2 | Presentation | Rory, Marco | 2020-03-14 | 2020-03-16 | 2 | 100% | bar: WEEK 9 S to WEEK 9 U
6.5 | Gantt Chart Update | Dasom | 2020-03-09 | 2020-03-16 | 7 | 100% | bar: WEEK 9 S to WEEK 9 U
7 | Team Sprint #7 |  | 2020-03-16 | 2020-03-30 | 14 | 100% | bar: WEEK 10 M to WEEK 11 U
7.1 | Team Meeting | All | 2020-03-23 | 2020-03-24 | 1 | 100% | bar: WEEK 11 M
7.2 | Update Prototype | Uday | 2020-03-23 | 2020-03-24 | 1 | 100% | bar: WEEK 11 M
7.3 | Implementation | See Below | 2020-03-16 | 2020-03-30 | 14 | 100% | bar: WEEK 10 M to WEEK 11 U
7.3.1 | Search Page - Fetch Data & Search | Uday | 2020-03-16 | 2020-03-23 | 7 | 100% | bar: WEEK 10 M to WEEK 10 U
7.3.2 | Search Page - Table & Dropdown | Dasom | 2020-03-16 | 2020-03-23 | 7 | 100% | bar: WEEK 10 M to WEEK 10 U
7.3.3 | Search API Research & Update (Dstu3) | Patrick | 2020-03-23 | 2020-03-30 | 7 | 100% | bar: WEEK 11 M to WEEK 11 U
7.3.4 | Add Dashboard to support 2 pages | Uday | 2020-03-23 | 2020-03-30 | 7 | 100% | bar: WEEK 11 M to WEEK 11 U
7.3.5 | Charts Page (Pie Chart & Bar Chart) | Marco | 2020-03-23 | 2020-03-30 | 7 | 100% | bar: WEEK 11 M to WEEK 11 U
7.4 | Dev Progress Check with TA | Dasom | 2020-03-25 | 2020-03-26 | 1 | 100% | bar: WEEK 11 W
7.5 | Status Update Report | Dasom | 2020-03-28 | 2020-03-30 | 2 | 100% | bar: WEEK 11 S to WEEK 11 U
7.5.1 | Gantt Chart Update | Dasom | 2020-03-23 | 2020-03-30 | 7 | 100% | bar: WEEK 11 M to WEEK 11 U
8 | Team Sprint #8 |  | 2020-03-30 | 2020-04-06 | 6 | 100% | bar: WEEK 13 M to WEEK 13 U
8.1 | Team Meeting | All | 2020-03-30 | 2020-03-31 | 1 | 100% | bar: WEEK 13 M
8.2 | Implementation - See Below | See Below | 2020-03-30 | 2020-04-06 | 6 | 90% | bar: WEEK 13 M to WEEK 13 U
8.2.1 | API Update and Research - Continued | Patrick | 2020-03-30 | 2020-04-06 | 6 | 100% | bar: WEEK 13 M to WEEK 13 U
8.2.2 | Search Page Update | Dasom | 2020-03-30 | 2020-04-06 | 6 | 100% | bar: WEEK 13 M to WEEK 13 U
8.2.3 | Chart Page Update | Marco | 2020-03-30 | 2020-04-06 | 6 | 100% | bar: WEEK 13 M to WEEK 13 U
8.3 | Gantt Chart Update/Status Report | Dasom | 2020-03-29 | 2020-03-30 | 1 | 100% | bar: WEEK 13 U
8.4 | Dev Progress Check with TA | Dasom | 2020-03-25 | 2020-03-26 | 1 | 100% | bar: WEEK 13 W
9 | Team Sprint #9 |  | 2020-04-06 | 2020-04-13 | 7 | 100% | bar: WEEK 14 M to WEEK 14 U
9.1 | Team Meeting | All | 2020-04-06 | 2020-04-07 | 1 | 100% | bar: WEEK 14 M
9.2 | Gantt Chart Update | Dasom | 2020-04-11 | 2020-04-13 | 2 | 100% | bar: WEEK 14 S to WEEK 14 U
9.3 | Sprint 9 Report | Dasom | 2020-04-11 | 2020-04-13 | 2 | 100% | bar: WEEK 14 S to WEEK 14 U
9.4 | Impelementation | See Below | 2020-04-06 | 2020-04-13 | 7 | 100% | bar: WEEK 14 M to WEEK 14 U
9.4.1 | Processing Data & med dispense | Patrick | 2020-04-06 | 2020-04-09 | 3 | 100% | bar: WEEK 14 M to WEEK 14 W
9.4.2 | Dashboard page - Implement charts | Dasom, Patrick | 2020-04-09 | 2020-04-13 | 4 | 100% | bar: WEEK 14 R to WEEK 14 U
9.4.3 | Search page - Modify search features | Dasom | 2020-04-09 | 2020-04-13 | 4 | 100% | bar: WEEK 14 R to WEEK 14 U
9.4.4 | Landing Page - Description about app | Patrick, Uday, Dasom | 2020-04-12 | 2020-04-13 | 1 | 100% | bar: WEEK 14 F to WEEK 14 U
9.4.5 | Adding Footer | Uday | 2020-04-10 | 2020-04-12 | 2 | 100% | bar: WEEK 14 F to WEEK 14 S
9.5 | Confirm Application Works | All | 2020-04-12 | 2020-04-13 | 1 | 100% | bar: WEEK 14 U
10 | Team Sprint #10 |  | 2020-04-13 | 2020-04-20 | 7 | 100% | bar: WEEK 15 M to WEEK 15 U
10.1 | Sprint 10 Report - Section I & II | Dasom | 2020-04-13 | 2020-04-14 | 1 | 100% | bar: WEEK 15 M
10.2 | Section III - Final Presentation | See Below | 2020-04-13 | 2020-04-16 | 3 | 100% | bar: WEEK 15 M to WEEK 15 W
10.2.1 | Introduction | Dasom | 2020-04-13 | 2020-04-16 | 3 | 100% | bar: WEEK 15 M to WEEK 15 W
10.2.2 | Research | Marco | 2020-04-13 | 2020-04-16 | 3 | 100% | bar: WEEK 15 M to WEEK 15 W
10.2.3 | About Project | Uday | 2020-04-13 | 2020-04-16 | 3 | 100% | bar: WEEK 15 M to WEEK 15 W
10.2.4 | Demonstration | Patrick | 2020-04-13 | 2020-04-16 | 3 | 100% | bar: WEEK 15 M to WEEK 15 W
10.2.5 | Project Status & Future Plan | Rory | 2020-04-13 | 2020-04-16 | 3 | 100% | bar: WEEK 15 M to WEEK 15 W
10.2.6 | Processing & Uploading Video | Dasom | 2020-04-15 | 2020-04-16 | 1 | 100% | bar: WEEK 15 W
10.3 | Section IV Project Documentation | See Below | 2020-04-13 | 2020-04-18 | 5 | 100% | bar: WEEK 15 M to WEEK 15 F
10.3.1 | Final Gantt Chart | Dasom | 2020-04-13 | 2020-04-18 | 5 | 100% | bar: WEEK 15 M to WEEK 15 F
10.3.2 | Application Manual | Uday | 2020-04-13 | 2020-04-18 | 5 | 100% | bar: WEEK 15 M to WEEK 15 F
10.3.3 | Special Instruction | Patrick | 2020-04-13 | 2020-04-18 | 5 | 100% | bar: WEEK 15 M to WEEK 15 F
10.3.4 | Research Material | Marco | 2020-04-13 | 2020-04-18 | 5 | 100% | bar: WEEK 15 M to WEEK 15 F
10.3.5 | Use Case Model | Dasom | 2020-04-13 | 2020-04-18 | 5 | 100% | bar: WEEK 15 M to WEEK 15 F
10.3.6 | Project Plan | Dasom | 2020-04-13 | 2020-04-18 | 5 | 100% | bar: WEEK 15 M to WEEK 15 F
10.3.7 | Design Document | Marco | 2020-04-13 | 2020-04-18 | 5 | 100% | bar: WEEK 15 M to WEEK 15 F
10.3.8 | Test Plan | Rory | 2020-04-13 | 2020-04-18 | 5 | 100% | bar: WEEK 15 M to WEEK 15 F
10.4 | Final Submission | Dasom | 2020-04-18 | 2020-04-19 | 1 | 100% | bar: WEEK 15 S
10.5 | Confirm Delivery of Final Product | All | 2020-04-19 | 2020-04-20 | 1 | 100% | bar: WEEK 15 U

## Try Smartsheet
Try Smartsheet for Free